## Calculate hours
Name of the task | OE optimistic estimation | OE realistic estimation | OE pesimistic estimation | Expected estimation Value
Analynics | 16 | 32 | 48 | 32
Application development and design | 120 | 140 | 160 | 140
Software testing | 10 | 15 | 25 | 15.8333
Advertising | 20 | 50 | 65 | 47.5
Release | 16 | 24 | 48 | 26.6667
Total |  |  |  | 262
Additional project cost
Item name | Expenses | Amount | Total
Computers | 400000 | 3 | 1200000
Office rent | 300000 | 2 | 600000
Utility bills | 20000 | 2 | 40000
Standart hosting | 30000 | 1 | 30000
Server's rent | 50000 | 2 | 100000
Coffee and tea | 10000 | 2 | 20000
Cookies | 15000 | 2 | 30000
Parking for employee | 5000 | 3 | 15000
Total |  |  | 2035000
Project per hours | 262 | hours
General labor rate | 1000 | tg/hour
Actual word hour per day | 8 | hour
Actual days per week | 5 | days
Week per month | 4 | week
Work productivity per month | 160 | W/H
Avialable workers per month | 2 | persons
Project effort | 1 | persons
Project configuration | 0.5 | persons
Total project effort | 3 | persons
Project duration | 2 | month
Project duration with additional efforts | 1.6 | month
Cost of project risks | 792000
Project labor cost | 256000
Total project cost | 3083000

## Risks
Identidied Risk Factor | Probability of Risk Factors | Impact of risk factor | Cost of risk factor
Fire | 1% | 3000000 | 30000
The uselessness of the application | 25% | 3000000 | 750000
Looting | 1% | 1200000 | 12000
Developer Burnout | 5% | 2000000 | 100000
Total |  |  | 792000